## Slide 1
Mars Global Mosaic
REMOTE SENSING 2026 OCN 4704
Logan Edwards
Interim Presentation · 42% complete

## Slide 2
Project Goals
Assemble a co-registered global visible and thermal-infrared mosaic of Mars in ArcGIS Pro from three existing global products, and use it to map and classify three landform families — volcanic flow units, fluvial channels and valley networks, and impact craters — producing one internally consistent global landform inventory.
Build one co-registered global visible + thermal-infrared mosaic of Mars in ArcGIS Pro.
Map and classify lava flow units, fluvial channels, and impact craters from it.
Test whether thermal infrared recovers flow boundaries that visible imagery misses under dust mantle.
Assess accuracy against the published USGS global geologic map and the IAU crater gazetteer — the only independent references available.

## Slide 3
Project Tasks and Percent Complete
# | Task | Complete | Progress
1 | Scope, targets, and type-area selection | 90% | ■■■■■■■■■
2 | Global raster acquisition — THEMIS, Viking, HRSC/MOLA | 100% | ■■■■■■■■■■
3 | Statistics and display stretches built (pyramids still not built) | 70% | ■■■■■■■
4 | Grouped mosaic viewer assembled (Viking / IR / HRSC MOLA) | 100% | ■■■■■■■■■■
5 | DEM terrain derivatives — slope and hillshade built | 80% | ■■■■■■■■
6 | Image-gradient products from THEMIS and Viking | 70% | ■■■■■■■
7 | Jezero context map — hosted rover services only, no held imagery | 20% | ■■
8 | Classification workflow — rehearsed on Mercury, not yet on Mars | 20% | ■■
9 | CRS harmonization to one projected frame | 15% | ■■
10 | Visible + infrared band composite | 5% | ■
11 | Landform digitizing — flows, channels, crater rims | 0% | –
12 | Crater inventory beyond the IAU gazetteer | 0% | –
13 | Map layouts and figure production | 0% | –
14 | Written report and presentations | 25% | ■■
Overall completion is approximately 42%. The base mosaic and its derived rasters are the gating tasks — classification, digitizing, and crater counting all wait on them.

## Slide 4
Processing Completed to Date
When | Tool | Parameters | Outcome
Sep 8, 18:34 | Iso Cluster + ML Classify | Mercury MESSENGER MDIS 166 m, 10 classes | Succeeded — method rehearsal on another body
Sep 9, 03:35 | Segment Mean Shift | Spectral detail 20, spatial detail 20, min segment 5 px | Succeeded
Sep 9, 11:52 | Composite Bands | Global extent | Failed — cancelled after 47 min 57 s
Sep 9, 12:43 | Composite Bands | Retry | Failed — cancelled after 1 min 41 s
Sep 9, 12:44 | Composite Bands | Retry | Failed — cancelled after 1 h 14 min 51 s
Sep 10, 19:44 | Slope → Slope_Mars_H1 | HRSC/MOLA DEM, percent rise, z-factor 1, planar | Succeeded in 7 min 15 s — WARNING 000869 (Z units undefined)
Sep 11, 12:03 | Slope → Slope_Mars_M1 | THEMIS Day IR, percent rise, z-factor 1, planar | Succeeded
Sep 11, 12:24 | Surface Parameters → Surface_Mars1 | Viking MDIM, slope, quadratic, 231.54 m fixed neighborhood | Succeeded in 1 h 26 min 45 s
Sep 11, 20:34 | Slope → Slope_Mars_V1 | Viking MDIM, percent rise, GPU then CPU | Succeeded in 1 h 05 min 01 s — no compatible GPU detected, ran on CPU
Sep 13, 03:03 | Hillshade → HillSha_Mars1 | HRSC/MOLA DEM, azimuth 225°, altitude 45°, shadows | Succeeded in 11 min 42 s — WARNING 000869 (Z units undefined)
Sep 13, 14:48 | Composite Bands | Global extent, first input Slope_Mars_V1 | Did not complete — output registered, no raster data written
Recovered from the geoprocessing lineage and tool logs in the project geodatabase — the actual run history, failures included.

## Slide 5
Relevant Spectral Bands
Band or product | Wavelength | Why this band
THEMIS Day IR (v12 mosaic) | 6.8–14.9 µm | The global morphology and composition base; the highest-resolution global layer held, at 100 m
Viking MDIM 2.1 band 1 (red) | ≈ 0.59 µm | Best contrast between ferric dust and darker basaltic surfaces
Viking MDIM 2.1 bands 1/2/3 | visible RGB | Natural-colour context and unit boundary confirmation; currently displayed with a 0.5% min-max stretch
HRSC/MOLA elevation | n/a (altimetry) | Absolute elevation; the vertical reference for every channel gradient measured
Derived: slope, percent rise | from elevation | Terrain slope for channel gradients and flow-front steepness
Derived: hillshade 225°/45° | from elevation | Shaded relief for visual interpretation of flow lobes and crater rims
Derived: THEMIS DN gradient | from thermal IR | Edge and texture measure — highlights thermal boundaries at flow margins
Derived: Viking DN gradient | from visible | Edge and texture measure — highlights albedo boundaries and crater rims
Planned: THEMIS day − night | 6.8–14.9 µm | Thermal inertia proxy; requires the night mosaic to be acquired

## Slide 6
Relevant Spectral Bands — by Region
Region | Wavelength | What it contributes
Visible | 0.4 – 0.7 µm | Viking MDIM 2.1 colour. Morphology, albedo contrast, and shadow relief; the ferric absorption edge separates bright dust from darker basaltic surfaces.
Thermal IR | 6.8 – 14.9 µm | THEMIS Day IR. Daytime brightness temperature carries both morphology and silicate composition through the Si–O reststrahlen bands.
Thermal IR (night) | 6.8 – 14.9 µm | THEMIS Night IR — not yet acquired. Paired with the day mosaic it yields thermal inertia, the single best dust-versus-bedrock discriminator from orbit.
Laser altimetry | 1064 nm (active) | HRSC/MOLA blended DEM. Not passive imaging, but it supplies the slope, gradient, and drainage context that separates channels from albedo streaks.
Held today: THEMIS Day IR as the 100 m morphology base, Viking MDIM 2.1 colour for visible context, and the HRSC/MOLA DEM for slope and drainage. THEMIS Night IR is the one missing band.

## Slide 7
Preliminary Results — Data and Measurements
Three global rasters loaded and characterized — THEMIS Day IR v12 at 100 m (22.14 billion valid pixels, DN 1–255, mean 125.7, σ 34.4), Viking MDIM 2.1 colour at 232 m (92,160 × 46,080), and the HRSC/MOLA blended DEM at 200 m. 43.7 GB of source imagery, with statistics built on all three; pyramids are not built on any of them.
Global relief measured directly from the DEM — Elevation ranges from −8,528 m to +21,226 m — a total relief of 29,754 m — with a mean of −720.5 m and σ of 2,976 m. The extremes fall where expected, at the Hellas basin floor and the Olympus Mons summit, which is a first confirmation that the DEM is correctly georeferenced.
Terrain derivatives built — Slope (percent rise) and hillshade (azimuth 225°, altitude 45°, shadows on) from the DEM, in 7 min 15 s and 11 min 42 s. Both currently carry WARNING 000869 and will be rebuilt on a projected DEM before any measurement is taken from them.

## Slide 8
Preliminary Results — Derived Products
Gradient products built from both image mosaics — Slope was run on the THEMIS and Viking rasters, giving DN gradient rather than terrain slope — an edge and texture measure. Surface Parameters was also run on the Viking mosaic with a quadratic fit over a 231.54 m fixed neighborhood, taking 1 h 26 min 45 s.
Classification workflow proven on another body — Iso Cluster with 10 classes followed by Maximum Likelihood, plus Segment Mean Shift (spectral 20, spatial 20, minimum segment 5 px), ran successfully end to end on the Mercury MESSENGER MDIS basemap. The method is proven; it has not yet been applied to the Mars stack.
One type area set up — The mosaic viewer is parked over western Valles Marineris (about 271–286°E, 6–13°S) — Ius Chasma and the Louros Valles tributaries on its south wall. A second map covers Jezero Crater, but it carries only hosted Perseverance rover services; no imagery of Jezero is held locally.
Every figure above was read from the project files themselves — raster statistics, geoprocessing lineage, and tool logs on Z:.

## Slide 9
Project Issues and Hurdles (1 of 2)
The project spans three coordinate frames — The DEM and its derivatives are in GCS_Mars_2000_Sphere (degrees). Viking and THEMIS are both SimpleCylindrical_Mars in metres, but on central meridians 0° and 180° respectively — the THEMIS grid runs 0–360°E, the other two −180–180°E. Read at face value the THEMIS window lands half a planet from the others. This is the root cause of both problems below. Fix: project everything into one frame and check the meridian, not just the units.
Terrain derivatives carry an invalid z-factor — Both DEM runs returned WARNING 000869 — metres of elevation against degrees of horizontal distance, default z-factor 1. Slope_Mars_H1 and HillSha_Mars1 are fine for display, not for measurement. They will be rebuilt after projection.
Composite Bands has failed three times — Three attempts on 9 September, abandoned after 47 min 57 s, 1 min 41 s, and 1 h 14 min 51 s. The visible + IR composite is the centrepiece of the project and does not yet exist. Plan: project to a common CRS and cell size, then run over bounded extents instead of the full globe.
No GPU acceleration on this machine — The Viking slope run requested GPU_THEN_CPU and logged 'No compatible GPU device has been detected', completing on CPU in 1 h 05 min. Every global run is CPU-bound, so processing time is effectively the project schedule.

## Slide 10
Project Issues and Hurdles (2 of 2)
Thermal inertia is blocked on a missing dataset — Only the THEMIS day mosaic is held. The dust-versus-bedrock argument needs the night mosaic for a diurnal difference. Same source and format as the day mosaic, so this is a download rather than a redesign — but it has not been done.
The crater layers cannot support crater dating — The IAU nomenclature gives 141 named craters above 100 km and 972 below. That is a gazetteer, not a crater-count inventory, and size-frequency dating cannot be done from it. Craters must be digitized in the type area or a catalogue imported.
Three dead raster references — The Jezero HiRISE orthomosaic, the Mercury MESSENGER basemap, and the Enceladus DEM are still referenced by their maps, but none of those files is on the drive. The three global rasters are the whole of the held imagery. None of the three is needed for the plan as scoped; they should be removed so the project opens clean.
Housekeeping — The nomenclature layers were imported more than once — 14 feature classes where five would do (_2 and _3 duplicates of four of them, _2 of the fifth) — and no map layouts exist in the project yet. Neither blocks analysis, but both need clearing before the final deliverables.

## Slide 11
Remaining Work — Immediate Next Steps
Project all three global rasters into one SimpleCylindrical_Mars frame at a common cell size and a common central meridian — THEMIS is on 180° and the other two on 0°. This unblocks everything else.
Rebuild Slope and Hillshade on the projected DEM so the z-factor is valid.
Retry Composite Bands over a bounded extent rather than the globe, and confirm the four-band stack is usable before scaling up.
Download the THEMIS Night IR global mosaic and difference it against the day mosaic.
Apply the Mercury classification workflow — Iso Cluster then Maximum Likelihood — to the Mars composite.
Rename the DN gradient products so they are not mistaken for terrain slope.
Delete the duplicate _2 and _3 nomenclature imports.
Build pyramids on the three global TIFFs — none of them has overviews, so every pass reads them at full resolution.
Remove the three dead raster references (HiRISE, Mercury, Enceladus) so the project opens without broken layers.
Start digitizing flow margins and channel centerlines in the Valles Marineris window.

## Slide 12
Remaining Schedule
Week | Dates (2026) | Activity | Deliverable
5 | Sep 21 – Sep 25 | Composite Bands over bounded extents; acquire THEMIS Night IR | Visible + IR composite raster
6 | Sep 28 – Oct 2 | Day–night thermal difference; training polygons | Thermal inertia proxy
7–8 | Oct 5 – Oct 16 | Iso Cluster and Maximum Likelihood classification of the Mars stack | Interim presentation; classified raster
9–10 | Oct 19 – Oct 30 | Digitize lava flow margins, channel centerlines, crater rims | Landform feature classes
11–12 | Nov 2 – Nov 13 | Crater inventory and size-frequency distributions in the type area | Crater database
13 | Nov 16 – Nov 20 | Accuracy assessment against a published geologic map | Confusion matrix
14 | Nov 23 – Nov 27 | Map layouts and figure production (Thanksgiving week — front-load into week 13) | Map sheets
15 | Nov 30 – Dec 4 | Final presentation and written report | Final deliverables
The critical path runs through weeks 5–8: nothing can be classified until the composite exists, and nothing can be digitized until it is classified.