Remote Sensing Project Prospectus

Mars Global Mosaic: Mapping Lava Flows, Fluvial Channels, and Impact Craters in Visible and Infrared

Logan Edwards

REMOTE SENSING 2026 OCN 4704

Fall 2026

Introduction:

Background: statement of goals and mission

Assemble a co-registered global visible and thermal-infrared mosaic of Mars in ArcGIS Pro from three existing global products, and use it to map and classify three landform families — volcanic flow units, fluvial channels and valley networks, and impact craters — producing one internally consistent global landform inventory.

Three global products already cover Mars end to end at better than 250 m per pixel, in three different parts of the spectrum: Viking MDIM 2.1 colour (visible, 232 m), THEMIS Day IR (thermal infrared, 100 m), and the HRSC/MOLA blended DEM (topography, 200 m). All three are downloaded and loaded.

They are distributed separately and in two different coordinate systems, so no single product lets you interrogate morphology, thermal response, and slope at the same pixel. Building that stack is the core technical task of this project.

The three target landform families each record a different process: volcanic resurfacing, flowing water, and impact. Each is expressed differently across the three datasets, which is what makes a fused stack worth building.

The methods are the same ones used for terrestrial scenes — band compositing, gradient and slope derivatives, unsupervised and supervised classification, accuracy assessment — applied to a planetary surface with no water column and no vegetation to correct for.

Tasks required to accomplish the goal and meet the mission

Ten tasks carry the project from the data already on disk to a finished landform map. They are ordered by dependency, not by effort. Tasks 1 and 2 are complete. Task 3 — putting every layer into one coordinate system — is the gate: the band composite in task 5 has already failed three times without it, and everything downstream of task 5 waits on that composite.

| # | Task | What it involves |
| --- | --- | --- |
| 1 | Acquire the global raster set | Viking MDIM 2.1 colour (232 m), THEMIS Day IR v12 (100 m), HRSC/MOLA blended DEM (200 m). All three are on disk with statistics built. Pyramids are not built on any of them, which is worth doing before the next global run. |
| 2 | Build a grouped mosaic viewer | One map holding three groups (Viking, IR, HRSC MOLA), each pairing the source raster with its derived product, so layers can be swapped against each other. Complete. |
| 3 | Harmonize the coordinate systems | Three frames, not two: the DEM is in GCS_Mars_2000_Sphere (degrees, central meridian 0); Viking is SimpleCylindrical_Mars in metres on central meridian 0; THEMIS is SimpleCylindrical_Mars in metres on central meridian 180. Project everything into one frame, and check the meridian, not just the units. |
| 4 | Rebuild the terrain derivatives correctly | Re-run Slope and Hillshade on the projected DEM so the z-factor is valid; the current versions were computed against degree units and carry WARNING 000869. |
| 5 | Build the visible + infrared composite | Composite Bands over the co-registered Viking colour and THEMIS Day IR — four bands. Elevation stays a separate analysis layer: Iso Cluster measures distance in raw band values, so a band running −8,528 to +21,226 m would swamp four running 1–255. Three attempts at global scale on 9 September, all cancelled before completing; the fix is to project first and run over bounded extents. |
| 6 | Derive image-gradient products | Slope on the THEMIS and Viking rasters is a DN gradient, not terrain slope — an edge and texture measure that highlights flow margins and crater rims. Label and use it as such. |
| 7 | Classify surface units | Iso Cluster unsupervised classification, then Maximum Likelihood against training polygons. The workflow has already been rehearsed end to end on the Mercury MESSENGER basemap; apply it to the Mars stack. |
| 8 | Digitize landform vectors | Lava flow margins, channel centerlines, and crater rims as three feature classes in the project geodatabase. |
| 9 | Build a real crater inventory | The IAU nomenclature layers already loaded are a gazetteer of 1,113 named craters, not a crater-count database. Either digitize craters in the type area or import a published catalogue. |
| 10 | Produce the map layouts | No layouts exist in the project yet. Global sheets plus detail panels for the two saved views: the Ius Chasma type area and the Jezero context map. |

Significance and importance of the mission

The fusion is the contribution. The three source products are individually standard, but stacking them into one analysis raster in a common projection is what allows a unit to be described by morphology, thermal response, and slope simultaneously.

Thermal infrared responds to particle size and surface coherence, which visible albedo does not. Where Mars is dust-mantled, the THEMIS layer should recover flow boundaries the Viking colour mosaic cannot — a claim this project can measure.

Discriminating volcanic from fluvial channels is a live problem: Athabasca Valles was mapped as a fluvial outflow channel for decades before being reinterpreted as flood lava. Morphology plus thermal response addresses it.

The workflow transfers terrestrial remote sensing methods to a planetary target with no water column and no vegetation, and only ~6 mbar of CO₂ overhead — the signal is almost entirely surface physics.

The result is testable without any privileged data. Unit boundaries can be checked against the published USGS global geologic map of Mars, and crater-rim detection against the 141 IAU-named craters above 100 km already in the geodatabase. Both are free, and neither depends on imagery this project does not hold.

Methods

Which part of the electromagnetic spectrum can be applied in the mission

Four regions of the spectrum carry usable information about the three target landform families. Each answers a different question, and the project depends on using them together rather than choosing among them.

| Region | Wavelength | What it contributes to the mission |
| --- | --- | --- |
| Visible | 0.4 – 0.7 µm | Viking MDIM 2.1 colour. Morphology, albedo contrast, and shadow relief; the ferric absorption edge separates bright dust from darker basaltic surfaces. |
| Thermal IR | 6.8 – 14.9 µm | THEMIS Day IR. Daytime brightness temperature carries both morphology and silicate composition through the Si–O reststrahlen bands. |
| Thermal IR (night) | 6.8 – 14.9 µm | THEMIS Night IR — not yet acquired. Paired with the day mosaic it yields thermal inertia, the single best dust-versus-bedrock discriminator from orbit. |
| Laser altimetry | 1064 nm (active) | HRSC/MOLA blended DEM. Not passive imaging, but it supplies the slope, gradient, and drainage context that separates channels from albedo streaks. |

The martian atmosphere is ~6 mbar of CO₂. It is effectively transparent across the visible and near-infrared; the THEMIS bands are placed to avoid the strong 15 µm CO₂ band.

Radar sounding (SHARAD, MARSIS) is deliberately excluded: it probes the subsurface rather than surface landforms, and has no global coverage at the resolution this project needs.

Potential remote sensing data sources

Every dataset below is public and free, served as GeoTIFF, which ArcGIS Pro ingests directly — no ISIS preprocessing is required. The first table is what is already downloaded and loaded into the project; the properties given were measured from the files themselves rather than quoted from the product documentation.

| Dataset | Mission | Type | Resolution | Measured properties |
| --- | --- | --- | --- | --- |
| Mars_MO_THEMIS-IR-Day_mosaic_global_100m_v12.tif | Mars Odyssey THEMIS | Thermal IR, 1 band, 8-bit | 100 m/px | 213,390 × 106,696 px; 22.14 of 22.77 billion valid (97.3% coverage); DN 1–255, mean 125.7, σ 34.4 |
| Mars_Viking_MDIM21_ClrMosaic_global_232m.tif | Viking Orbiter | Visible colour, 3 bands | 232 m/px | 92,160 × 46,080 px; band 1 DN 18–207, mean 122.8, σ 31.6 |
| Mars_HRSC_MOLA_BlendDEM_Global_200mp_v2.tif | Mars Express / MGS | Elevation, 1 band, 16-bit | 200 m/px | 106,694 × 53,347 px; −8,528 m to +21,226 m, mean −720.5 m |
| MARS_nomenclature_* (5 feature classes) | IAU / USGS, March 2019 | Point and polygon gazetteer | n/a | 141 craters >100 km; 972 craters <100 km; 126 albedo; 303 classical albedo; 337 other |

The following are not yet acquired, and the project plan depends on them:

| Dataset | Resolution | Why it is needed |
| --- | --- | --- |
| THEMIS Night IR global mosaic | 100 m/px | The highest-value missing dataset. Same source and format as the day mosaic already held; day–night pairing is what turns brightness temperature into thermal inertia. |
| CTX mosaic tiles (bounded, not global) | 5–6 m/px | Needed only over the type area, to resolve channel margins and craters below the ~1 km limit of the 100 m base. A global CTX mosaic is multi-terabyte and is explicitly out of scope. |
| A crater catalogue or digitized crater layer | n/a | The IAU layers are named features only. Crater statistics need either a published catalogue or craters digitized in the type area. |

Which spectral bands

The band set is chosen so that each of the three landform families is addressed by at least two independent lines of evidence — one morphological and one spectral or thermophysical.

| Band or product | Wavelength | Why this band |
| --- | --- | --- |
| THEMIS Day IR (v12 mosaic) | 6.8–14.9 µm | The global morphology and composition base; the highest-resolution global layer held, at 100 m |
| Viking MDIM 2.1 band 1 (red) | ≈ 0.59 µm | Best contrast between ferric dust and darker basaltic surfaces |
| Viking MDIM 2.1 bands 1/2/3 | visible RGB | Natural-colour context and unit boundary confirmation; currently displayed with a 0.5% min-max stretch |
| HRSC/MOLA elevation | n/a (altimetry) | Absolute elevation; the vertical reference for every channel gradient measured |
| Derived: slope, percent rise | from elevation | Terrain slope for channel gradients and flow-front steepness |
| Derived: hillshade 225°/45° | from elevation | Shaded relief for visual interpretation of flow lobes and crater rims |
| Derived: THEMIS DN gradient | from thermal IR | Edge and texture measure — highlights thermal boundaries at flow margins |
| Derived: Viking DN gradient | from visible | Edge and texture measure — highlights albedo boundaries and crater rims |
| Planned: THEMIS day − night | 6.8–14.9 µm | Thermal inertia proxy; requires the night mosaic to be acquired |

Resolution required — spatial, spectral, radiometric, temporal

Spatial

The global base is set by what is held: 100 m (THEMIS), 200 m (DEM), 232 m (Viking). The composite can be no finer than the coarsest input unless the others are resampled up.

Working rule: roughly ten pixels across a feature are needed to map its margin reliably. At 100 m that means features ≥ 1 km — adequate for flow lobes and trunk valleys, but sub-kilometre tributaries will not resolve.

That limit is the argument for bounded CTX windows at 5–6 m over the type area rather than a finer global sheet. No sub-metre imagery is held, so everything below about a kilometre is a stated limit of the mapping rather than something this project can resolve.

Spectral

Held: one thermal band (THEMIS day) plus three visible bands (Viking). That is four bands total — enough to discriminate broad unit types, not enough to identify minerals.

Adding THEMIS Night IR is the single highest-value spectral addition, because it converts the existing day mosaic into a thermophysical measurement rather than just an image.

Mineral identification would require CRISM, which ArcGIS Pro cannot process as hyperspectral cubes. Out of scope; noted as a limitation rather than a plan.

Radiometric

THEMIS and Viking are both 8-bit as distributed — adequate for morphology and for the visual mosaic, and the practical constraint on how finely surface units can be separated by DN alone.

The DEM is the exception: it carries a real physical range of −8,528 m to +21,226 m, a relief of 29,754 m, which is where the quantitative measurements in this project will come from.

Deriving true thermal inertia would require calibrated radiance rather than the 8-bit mosaic. The day–night difference approach is therefore a proxy, and will be described as one.

Temporal

Martian landforms do not change on human timescales, so temporal resolution is not about change detection here.

It matters diurnally: day and night IR of the same ground is the entire basis of the planned thermal inertia product.

It matters seasonally in the source mosaics, which are already composited from many orbits selected for low dust opacity — an upstream decision inherited rather than controlled.

The one genuinely time-varying layer is the Perseverance traverse feature service in the Jezero context map, which updates as the rover drives. It is a hosted web service rather than held data, so it needs a network connection.

Project schedule

| Week | Dates (2026) | Activity | Deliverable |
| --- | --- | --- | --- |
| 1–2 | Aug 24 – Sep 4 | Scoping; target and type-area selection | Target list |
| 3 | Sep 7 – Sep 11 | Global raster acquisition; first derivatives (slope, surface parameters) | Three global rasters loaded |
| 4 | Sep 14 – Sep 18 | Project all layers to SimpleCylindrical_Mars; rebuild DEM derivatives with a valid z-factor | Single-CRS layer stack |
| 5 | Sep 21 – Sep 25 | Composite Bands over bounded extents; acquire THEMIS Night IR | Visible + IR composite raster |
| 6 | Sep 28 – Oct 2 | Day–night thermal difference; training polygons | Thermal inertia proxy |
| 7–8 | Oct 5 – Oct 16 | Iso Cluster and Maximum Likelihood classification of the Mars stack | Interim presentation; classified raster |
| 9–10 | Oct 19 – Oct 30 | Digitize lava flow margins, channel centerlines, crater rims | Landform feature classes |
| 11–12 | Nov 2 – Nov 13 | Crater inventory and size-frequency distributions in the type area | Crater database |
| 13 | Nov 16 – Nov 20 | Accuracy assessment against a published geologic map | Confusion matrix |
| 14 | Nov 23 – Nov 27 | Map layouts and figure production (Thanksgiving week — front-load into week 13) | Map sheets |
| 15 | Nov 30 – Dec 4 | Final presentation and written report | Final deliverables |

Semester dates are assumed and should be adjusted to the syllabus. Weeks 1 to 3 are complete. The critical path runs through weeks 4 to 8: projecting every layer into one coordinate system unblocks the band composite, and the composite unblocks classification, digitizing, and everything downstream of them.

Expected results

Hypotheses to be tested

H1. In dust-mantled regions, the THEMIS Day IR layer will delineate volcanic flow boundaries that are not visible in the Viking colour mosaic, because thermal response depends on particle size and surface coherence while visible albedo is dominated by the dust veneer. Measured as mapped flow area from the IR layer versus the visible layer over the same extent.

H2. Channel segments classed as fluvial will show shallower longitudinal gradients in the HRSC/MOLA DEM than segments classed as volcanic, and the two populations will separate when gradient is plotted against thermal DN.

H3. A four-band composite (Viking R/G/B + THEMIS day) will produce more stable Iso Cluster classes than any single input, measured by how many of the requested classes survive with a meaningful pixel count.

H4. Crater rim detection from the DN gradient products will recover a large majority of the 141 IAU-named craters larger than 100 km, giving an independent check on the gradient method before it is trusted on unnamed craters.

Questions to be answered

Does projecting the DEM into SimpleCylindrical_Mars on a common central meridian, and re-running Slope with a valid z-factor, change the slope values enough to alter any interpretation?

Once the three frames are harmonised onto one meridian, does Composite Bands complete at global scale, or is a tiled, bounded-extent workflow still the only viable path on this hardware?

How much does the 8-bit depth of the THEMIS and Viking mosaics limit how finely surface units can be separated?

Is the day-only THEMIS mosaic sufficient to separate flows from dust, or is the night mosaic genuinely required?

At 100 m, how many orders of tributary in a valley network are recoverable, and where does the count saturate?

The DN gradient reproduces Viking mosaic seams as false edges. Setting those aside, does it reveal any unit boundary the source image does not already show — or is its only real use as an edge mask?

Potential problems that may be encountered

Each problem below is paired with the mitigation already planned for it. Several are expected to constrain the final result rather than be eliminated; where that is true, it is stated.

Three coordinate frames in one project. The HRSC/MOLA DEM and its derivatives sit in GCS_Mars_2000_Sphere (degrees); Viking and THEMIS both sit in SimpleCylindrical_Mars (metres) but on different central meridians — Viking on 0°, THEMIS on 180°, so the THEMIS grid runs 0–360°E while the other two run −180–180°E. A stack built without fixing that would be half a planet out and would misregister silently rather than fail. Mitigation: project everything to one frame and verify the meridian. This is the root cause of the next two problems.

Invalid z-factor on the terrain derivatives. Both DEM-derived runs returned WARNING 000869 — vertical units in metres against horizontal units in degrees, with a default z-factor of 1. The existing Slope_Mars_H1 and HillSha_Mars1 are usable for display but not for measurement. Mitigation: rebuild them on the projected DEM.

Composite Bands does not complete at global scale. Three attempts on 9 September, cancelled after 47 min 57 s, 1 min 41 s, and 1 h 14 min 51 s — the tool logs record all three as cancelled by the user, not as tool errors. The visible + IR composite is the centrepiece of the project and it does not yet exist. Mitigation: project to a common CRS and cell size first, then run over bounded extents rather than the full globe.

Processing time is the schedule. Measured runtimes on this machine: 7 min for slope on the 200 m DEM, 12 min for hillshade on the same DEM, 1 h 05 min for slope on the 232 m Viking mosaic, 1 h 27 min for surface parameters. ArcGIS Pro reported no compatible GPU on the one run that requested one, so every tool runs on CPU. Mitigation: budget whole evenings for global runs and prototype on subsets.

The crater layers are a gazetteer, not an inventory. The IAU nomenclature holds 141 craters above 100 km and 972 below — 1,113 named features in total, against the hundreds of thousands of craters on Mars larger than 1 km. Crater size-frequency dating cannot be done from these layers. Mitigation: digitize craters in the type area or import a published catalogue.

“Slope” on imagery is not slope. Slope_Mars_M1 and Slope_Mars_V1 were computed from THEMIS and Viking brightness values, not elevation. They are DN gradient — a legitimate edge and texture measure, but not terrain. Mitigation: rename and describe them as gradient products so no reader mistakes them for topography.

Thermal inertia is not yet possible. Only the THEMIS day mosaic is held. Without the night mosaic there is no diurnal difference, and the dust-versus-bedrock argument rests on a single daytime image. Mitigation: acquire the night mosaic — same source and format, so this is an afternoon of downloading, not a redesign.

No pyramids on the global rasters. None of the three source TIFFs carries overviews — one image level each, and no .ovr sidecar. Every redraw and every global tool pass therefore reads full resolution, including a 22.8-billion-pixel thermal mosaic. Mitigation: build pyramids once, before the next global run; it is the cheapest speed-up available on CPU-only hardware.

8-bit source depth. Both image mosaics are 8-bit, so subtle DN differences between dusty units may simply not be recorded. Mitigation: treat classification boundaries as coarse and do not over-interpret single-DN differences.

Unsupervised classification may collapse. Iso Cluster tends to return far fewer classes than requested when a large background or nodata region dominates the histogram. Mitigation: mask nodata first, run over bounded windows, and over-request classes.

No ground truth, and no sub-metre imagery. Validation is against published interpretations, not field data, and the finest imagery held is 100 m. Nothing in this project can confirm a landform below about a kilometre. Mitigation: assess accuracy against the published USGS global geologic map and the IAU crater gazetteer, and state the resolution limit as a limit rather than working around it.